## Лист1
Date | Толя | Саня | Сашко | Ваня | Ден | Міша | Оксана | Аня
2014-04-18 | 1. Написав першу робочу версію ServiceRefresh 2.Налаштував разом з Санею К. Realm Security на проді, тепере авторизація працює і там 3.Вбив 2,5 год. щоб залити собі репозиторій, зі своїм мобільним інтернетом(знаю, сам винний, що поїхав додому)
2014-04-22 | [7 empty] | 1.Війна з ajax, який постійно і нагло викидує Ajax error 2.Розробка CSE Dashboard (його готовність на перерішній час складає 7%)
2014-04-24 | SAD - 80% TracibilityMatrix - 100% DAO - 90% Integration with Google Map API - 75% e2e сценарій - 15% PEDashboards - 10% | Reports - 85% Production server - 100% e2e scenario - 15% PE Dashboard - 10% Logging (Log4j) - 90% | Test Data - 99% E-mail - 90% Sequaence diagrams - 30% | Изучал Google API для реализации определения оптимального Provider Location для Service Location. Сервис реализующий функционал - Distance Matrix API. |  | Test cases - 100% Test sequences - 80% Test strategy -100% | DAO - 90% mail - 90% CSEdashboard - 10% pagination - 30%(working now on it) | TracibilityMatrix - 100% Use Cases -95% CSEdashboard - 10% pagination - 30%
2014-04-25 | e2e сценарій - 25% DAO - 92% | Reports - 90% Logging (Log4j) - 95% | Sequaence diagrams - 55% | e2e, service order creating (map)- 40% |  | Test sequences - 100% | CSEdashboard - 15% pagination - 40% | CSEdashboard - 12% pagination - 32%
2014-04-26 | e2e сценарій - 35% DAO - 95% | Reports - 92% Logging (Log4j) - 100% SO e2e scenario - 35 % | IEDashboard - 3% | e2e, service order creating (map)- 60% |  | IEDashboard - 3% | CSEdashboard-20% DAO - 95% | CSEdashboard - 15% pagination & paging- 40% done problems with server
2014-04-27 | [7 empty] | CSEdashboard - 25% pagination & paging- 60%